## Execution Status
TEST EXECUTION STATUS
Project Name |  | Mobile QA Assignment
Module |  | Search Functionality
Report Date |  | 2017-12-03
Planned Completion Date |  | 2017-12-03
Execution Summary
Total Test Cases | Out of Scope | In Scope | Blocked | No Run | Passed | Failed | Executed | Test Coverage (%) | Pass Percentage (%)
7 | 0 | 7 | 0 | 7 | 4 | 3 | 7 | 100 | 57.14
Defect Summary
Defect Count | New | Open | Fix-in-Progress | Fixed | Retest | Deferred | Closed | Withdrawn | Rejected
P1-Critical | 1
P2-High | 1
P3-Medium
P4-Low | 1
Overall Execution Summary
Requirement ID | Test Case ID | Test Case Name |  | Planned Date | Execution Date | Status | Complexity | Responsible Tester | Defect ID | Defect Description | Severity
R001 | TC01 | Verify that the user is able to launch and then close the application "Mobile Assignment" |  | 2017-12-03 | 2017-12-03 | Pass | Simple | Madhur
R001 | TC02 | Verify that a Search Text box is present on opening the application |  | 2017-12-03 | 2017-12-03 | Pass | Simple | Madhur
R001 | TC03 | Verify that no results are displayed on the search result screen |  | 2017-12-03 | 2017-12-03 | Fail | Simple | Madhur | 1 | Junk values or recent searches displayed on the result screen even before entering anything on the search criteria | P4
R001 | TC04 | Verify that the user is able to enter the text on the search text box |  | 2017-12-03 | 2017-12-03 | Pass | Simple | Madhur
R001 | TC05 | Verify that a list of suggested cities is displayed as per the entered text on the search textbox |  | 2017-12-03 | 2017-12-03 | Pass | Medium | Madhur
R001 | TC06 | Verify that the user is able to select the city from the list of suggested cities on the result screen |  | 2017-12-03 | 2017-12-03 | Fail | Complex | Madhur | 2 | 1) The name of the city or place searched is not displayed on the maps 2) The pin also didn't point to the place we seaqrched and selected from the search text box | P1
R001 | TC07 | Verify that no search results are displayed when user enters invalid or special characters or numbers (Negative Scenario) |  | 2017-12-03 | 2017-12-03 | Fail | Medium | Madhur | 3 | 1) No place displayed on the result screen when a house number is added before the place to be searched 2) No records were displayed when exact search criteria was given along with Country code (for example - Amsterdam , NL) 3) Also no suggestions/reseults were displayed when a place was mentioned and the country code was kept blank (for example - Amsterdam) | P2