## Evaluation Report
PROJECT EVALUATION REPORT
Project Name |  |  |  | Mobile QA Assignment
Project Description |  |  |  | An android application that locates city on map useful for navigation purpose
Report Date |  |  |  | 2017-12-03
Planned Completion Date |  |  |  | 2017-12-08
Scope Covered |  |  |  | Testing of a search function for the android application-Mobile Assignment
Test Phase |  |  |  | Planned Start Date | Planned Completion |  | Actual Start Date | Actual Completion | Status
Test Preparation |  |  |  | 2017-12-01 | 2017-12-01 |  | 2017-12-01 | 2017-12-01 | Completed
Test Environment |  |  |  | 2017-12-02 | 2017-12-02 |  | 2017-12-02 | 2017-12-02 | Completed
Test Execution (Cycle 1) |  |  |  | 2017-12-03 | 2017-12-03 |  | 2017-12-03 | 2017-12-03 | Completed
Test Execution (Cycle 2) |  |  |  | 2017-12-04 | 2017-12-04 |  |  |  | In Future
Execution Summary
Total Test Cases |  | Out of Scope |  | In Scope | Blocked |  | No Run | Executed | Passed |  | Failed |  | Test Coverage |  | Pass Percentage
7 |  | 0 |  | 7 | 0 |  | 0 | 7 | 4 |  | 3 |  | 100% |  | 57.14%
Defect Details
Defect ID |  | Status |  | Severity | Priority |  | Action On | Raised By | Test blocked |  | Description
1 |  | New |  | P1 | T1 |  | Backbase Dev | Madhur | 1 |  | 1) No place displayed on the result screen when a house number is added before the place to be searched 2) No records were displayed when exact search criteria was given along with Country code (for example - Amsterdam , NL) 3) Also no suggestions/reseults were displayed when a place was mentioned and the country code was kept blank (for example - Amsterdam)
2 |  | New |  | P2 | T2 |  | Backbase Dev | Madhur | 1 |  | 1) The name of the city or place searched is not displayed on the maps 2) The pin also didn't point to the place we seaqrched and selected from the search text box
3 |  | New |  | P4 | T4 |  | Backbase Dev | Madhur | 1 |  | Junk values or recent searches displayed on the result screen even before entering anything on the search criteria
Risk / Issues Log
Category |  | ID | Level | Description |  | Impact |  | Mitigation |  | Owner |  | Open Date |  | Closed Date |  | Status
Risk |  | R01 | High | Huge count of open defects |  | Impacting the test execution timelines of cycle 2 |  | Require prompt fixes to be delivered in test environment to achieve the test completion timelines of cycle 2 |  | Development Team |  | 2017-12-03 |  | - |  | Open
Issue |  | I01 | Medium | Response time of application to launch is slow |  | Impacting the testing window futher having cascading effects to timelines |  | 1) Reducing the number of records in database to reduce impact on functional testing 2) Separate performance testing to be scoped in at later stage |  | Performance Team |  | 2017-12-03 |  |  |  | Open
Recommendation
1 | Testing to be carried out on other android devices to validate the resolution of the app
2 | Application utility can be further expanded for IOS platforms